## Read Me
Guidebook Use | Quick Tips
This workbook is a 12-week adoption guide: one 45-minute session per tab. | Model curiosity: share one imperfect experiment first.
Leaders: skim each weekly tab before your session. The ‘Instructor Directions’ column is your playbook to shine. | Protect time: if playtime isn’t scheduled, it won’t happen.
Capture live notes in the Feedback tab. Paste selected rows into the Prompts to generate summaries and emails. | Name risks early; define controls together (reviewers, audit, rollback).
Keep scope small. Celebrate learning, not perfection. Adoption is a rhythm, not a rollout. | Credit skeptics who contribute — it builds durable trust.

## Week 1
Session Theme | Objectives | Agenda (45 min) | Materials | Instructor Directions | Discussion Prompts | Risks to Watch | Success Criteria | Follow-ups
Kickoff: Setting the Stage for AI Adoption | • Align on why we're exploring AI now (change management over tech rollout) • Normalize curiosity and questions; set tone of ‘learn together’ • Surface one real work area per person that could benefit from AI | 5 min — Welcome & context: Why adoption is a people project 10 min — Live demo: Simple, relatable AI use (e.g., summarizing a policy) 15 min — Round-robin: One task you'd make easier or faster 10 min — Agree on ground rules (psych safety, data do/don’t, sandbox) 5 min — Assign light experiment: Try one AI interaction before Week 2 | • Slides (optional) with ground rules and safe-use policy highlights • Live access to an approved AI tool • Note-capture doc or shared spreadsheet (use Feedback tab) | • Model humility: Share one thing AI confuses you about • Co-create the ground rules; don't read them at people • Invite one-word reactions to the demo to take pulse (e.g., 'curious', 'skeptical') | • What part of today’s work would you happily outsource to a ‘smart intern’? • What’s one outcome (not output) that AI might help us achieve? • What boundary do we need so people feel safe experimenting? | • Over-promising on efficiency before trust is built • Data copy/paste into tools without clarity on sensitivity • Equating curiosity with commitment — keep pressure low | • Ground rules agreed and posted • Each participant named a candidate task to test • Sentiment check recorded (e.g., word cloud from reactions) | • Share the ground rules and resources link • Confirm one micro-experiment per person before Week 2

## Week 2
Session Theme | Objectives | Agenda (45 min) | Materials | Instructor Directions | Discussion Prompts | Risks to Watch | Success Criteria | Follow-ups
Exploring Everyday AI Use Cases | • Showcase simple tools and low-risk workflows • Capture first impressions (wins, frictions, surprises) • Identify 1-2 department-specific ‘use case clusters’ | 5 min — Check-in: What did you try? One-sentence share 10 min — Demo: Drafting email, summarizing a page, synthesizing notes 15 min — Breakouts by function: Map 3 candidate tasks per group 10 min — Report-out and cluster themes 5 min — Decide which tasks to test in sandbox (Weeks 5–8) | • Short list of approved tools (with links) • Use-case cards or examples from your domain • Feedback tab ready for notes | • Capture ‘frictions’ explicitly — they inform guardrails • Praise skepticism that is specific (turns into design input) • Keep demos short, interactive, and relevant | • Where did AI feel helpful vs. distracting? • What would make your next experiment safer or clearer? • Which use cases seem shareable across teams? | • Performative buy-in (nods without engagement) • Tool sprawl without clarity on data boundaries | • 2–3 use case clusters identified per department • Specific frictions documented to inform policy | • Publish the ‘shortlist’ of sandbox tasks for Month 2 • Assign owners for each task

## Week 3
Session Theme | Objectives | Agenda (45 min) | Materials | Instructor Directions | Discussion Prompts | Risks to Watch | Success Criteria | Follow-ups
Understanding Stakeholder Perspectives | • Map roles most affected by AI changes • Elicit concerns and incentives per role • Draft first-pass personas (with ChatGPT) for adoption design | 5 min — Recap: Where AI might touch identity, status, or risk 15 min — Live persona creation in ChatGPT (role-by-role) 15 min — Group refine: What would build trust for each persona? 10 min — Decide on outreach/enablement tactics per role | • Role list by department • ChatGPT prompt template (see Prompts tab) | • Name the elephant: Some roles feel automated away — center trust • Translate ‘fear’ into design requirements (e.g., manual override, auditability) | • What would make this feel like a tool rather than a threat? • What decision rights must remain human? • What ‘proof of safety’ would each role need? | • Stereotyping personas — keep them grounded in your org’s reality • Skipping enablement for skeptics (they need *more*, not less) | • Personas drafted with clear trust-builders • Enablement tactics aligned to roles | • Share personas and invite async comments • Fold insights into sandbox design

## Week 4
Session Theme | Objectives | Agenda (45 min) | Materials | Instructor Directions | Discussion Prompts | Risks to Watch | Success Criteria | Follow-ups
Building a Culture of Curiosity | • Codify shared principles for experimentation • Make leader behaviors explicit (model curiosity, protect time) • Prepare for Month 2 sandbox launch | 10 min — Principles workshop: Draft 5–7 team norms 15 min — Leader modeling: Show a messy experiment and learnings 10 min — Define the sandbox rituals (cadence, channels, learning log) 10 min — Confirm Month 2 plan and owners | • Principles examples • Learning log template (use Feedback tab or your wiki) | • Choose *one* visible leader habit to start this week (e.g., ‘Friday Fumbles’) • Timebox decisions; perfect is the enemy of momentum | • What ritual will make curiosity durable here? • Where do we need a ‘do not use AI’ sign for now (compliance/data)? | • Principles that are posters, not practices — assign owners • No time protected for play — sandbox dies on impact | • Principles finalized and published • Sandbox cadence and channels created | • Announce Month 2 sandbox and expectations • Remind leaders of their modeling commitment

## Week 5
Session Theme | Objectives | Agenda (45 min) | Materials | Instructor Directions | Discussion Prompts | Risks to Watch | Success Criteria | Follow-ups
Launching the AI Playground (Sandbox) | • Clarify boundaries, approved tools, and success measures • Kick off low-stakes experiments tied to real tasks • Start the learning log habit | 10 min — Policy recap: Data rules, do/don’t examples 15 min — Team selects 1–2 experiments from shortlist 15 min — Plan experiments: who, what, how, evidence of learning 5 min — Commit in writing to Feedback tab | • Approved tool list with links • Experiment planning template (use Feedback tab columns) | • Ask for ‘evidence of learning’ not ‘proof of ROI’ • Keep scope tiny; aim for momentum over magnitude | • What’s the smallest step that would teach us the most? • How will we know we learned something useful? | • Shadow data use; re-iterate safe examples • Overengineering experiments | • At least one experiment per team committed • Learning log entries started | • DM owners mid-week to unblock • Capture quick video wins to share

## Week 6
Session Theme | Objectives | Agenda (45 min) | Materials | Instructor Directions | Discussion Prompts | Risks to Watch | Success Criteria | Follow-ups
Experimentation Round 1 | • Share early results (warts and all) • Distill surprises and blockers • Refine experiments for next week | 5 min — Lightning updates (60s each) 15 min — Show & tell: before/after artifacts 15 min — Group debrief: patterns, blockers, workarounds 10 min — Adjust next tests; log changes | • Screenshots or snippets of outputs • Feedback tab ready to capture patterns | • Normalize ‘failed’ experiments as progress • Extract one reusable prompt per team | • What would you try differently with the same task? • Where did human judgment add essential value? | • Tool-of-the-week distractions • Judgmental language that chills participation | • Blockers identified with owners • At least one re-usable prompt captured | • Share a mini ‘pattern library’ of prompts • Check compliance on any gray-area data

## Week 7
Session Theme | Objectives | Agenda (45 min) | Materials | Instructor Directions | Discussion Prompts | Risks to Watch | Success Criteria | Follow-ups
Experimentation Round 2 + Peer Sharing | • Deepen experiments and cross-pollinate ideas • Pair teams to give feedback • Capture candidate pilots | 10 min — Pairs exchange: demo & critique 15 min — Refactor prompts or workflow live 10 min — Identify what’s pilot-worthy vs. playground-only 10 min — Update Feedback tab with candidate pilots | • Pairing list • Prompt templates | • Keep critique kind, specific, and actionable • Ask ‘what problem did this actually solve?’ | • What made this transfer well to a different team? • What trust checks would a pilot need (QA, audit, reviewers)? | • Premature scaling without trust gates • Overfitting prompts to one person’s style | • 2–3 pilot candidates listed with rationale • Revised prompts documented | • Draft pilot charters for top candidates • Confirm reviewers and success gates

## Week 8
Session Theme | Objectives | Agenda (45 min) | Materials | Instructor Directions | Discussion Prompts | Risks to Watch | Success Criteria | Follow-ups
Identifying Early Wins | • Surface credible small wins (confidence builders) • Decide which wins to communicate org-wide • Prepare transition from sandbox to practice | 10 min — Win stories: what changed for real people 10 min — Evidence review: before/after artifacts 15 min — Comms plan: who needs to hear what 10 min — Shortlist 1–2 pilots to ready for Month 3 | • Artifacts, quotes, screenshots • Comms template (Prompts tab) | • Spotlight contributions by skeptics who engaged • Translate wins into human outcomes (clarity, speed, confidence) | • Which story would persuade a thoughtful skeptic? • What caveats must be shared to stay credible? | • Over-claiming impact from thin evidence • Skipping attribution; give credit generously | • Win stories drafted and approved • Pilot shortlist confirmed | • Publish internal post with wins • Set up pilot kickoffs for Month 3

## Week 9
Session Theme | Objectives | Agenda (45 min) | Materials | Instructor Directions | Discussion Prompts | Risks to Watch | Success Criteria | Follow-ups
From Play to Practice | • Select experiments ready for real workflows • Define decision rights, QA, and oversight • Plan lightweight adoption in one area | 10 min — Pilot candidate deep-dive 15 min — Define controls: reviewers, audit trails, rollbacks 10 min — Decide where to embed first 10 min — Document practice change in Feedback tab | • Pilot charter template • Risk/controls checklist | • Insist on explicit human-in-the-loop steps • Name exit criteria if the pilot underperforms | • What could go wrong and how will we catch it? • What training is required for the target workflow? | • Ambiguous ownership for QA • No rollback plan | • Pilot plan with owners and controls • Training needs logged | • Book training sessions • Prepare success/stop criteria doc

## Week 10
Session Theme | Objectives | Agenda (45 min) | Materials | Instructor Directions | Discussion Prompts | Risks to Watch | Success Criteria | Follow-ups
Cross-Team Learning | • Share pilots-in-progress to harvest patterns • Reduce duplication by aligning methods • Spot opportunities for shared components | 10 min — Pilot posters: 3-minute per team 15 min — Pattern harvest: prompts, workflows, controls 10 min — Consolidate into shared ‘starter kits’ 10 min — Assign maintainers | • Poster template • Starter kit repo/folder | • Ask ‘What can we standardize without stifling learning?’ • Capture 3–5 reusable assets | • Which patterns are generalizable vs. context-specific? • What enablement would let another team adopt this next week? | • Inconsistent controls across teams • Starter kits that no one maintains | • Shared assets published • Maintainers named | • Announce starter kits and where to find them • Schedule office hours

## Week 11
Session Theme | Objectives | Agenda (45 min) | Materials | Instructor Directions | Discussion Prompts | Risks to Watch | Success Criteria | Follow-ups
Measuring Progress (Beyond Efficiency) | • Define qualitative & lightweight quantitative signals • Assess confidence and collaboration shifts • Decide on ongoing measurement cadence | 10 min — Review learning log & pilot outcomes 15 min — Define 4–6 signals (e.g., time-to-draft, confidence rating) 10 min — Agree how to capture signals monthly 10 min — Draft scorecard outline | • Signal/metric menu • Scorecard template | • Keep measures human-centered and honest • Avoid vanity metrics that invite gaming | • What feels different about your work now? • Where is oversight still needed? | • Chasing ROI prematurely • Survey fatigue | • Signals selected and documented • Scorecard skeleton created | • Publish scorecard and owners • Schedule first readout

## Week 12
Session Theme | Objectives | Agenda (45 min) | Materials | Instructor Directions | Discussion Prompts | Risks to Watch | Success Criteria | Follow-ups
Reflect, Celebrate, and Plan Next Steps | • Consolidate learnings into a narrative • Decide what becomes ‘business as usual’ • Set priorities for the next 90 days | 10 min — Celebrations and shout-outs 15 min — Story of change: Before → After → Next 10 min — BAU candidates vs. retire/reshape 10 min — Top 3 priorities for next quarter | • Learning log highlights • Comms templates (Prompts tab) | • Make heroes of contributors (especially early skeptics) • Keep ‘next’ small, specific, and scheduled | • What stays, what evolves, what stops? • What support do we need to keep momentum? | • Letting the story die in files — tell it widely • No owner for BAU changes | • Change story drafted • Next 90-day priorities assigned | • Send summary email & publish artifacts • Book next quarter’s cadence

## Feedback
How to Use
Log notes live during or after each session. Keep items concrete and attributable.
Paste links to artifacts (screens, prompts, docs). Include brief context.
Capture at least one quote per week in participants’ own words.
Use ‘Confidence’ as a quick pulse. Low scores are valuable signals.
‘Next Step’ should be specific (owner + date).
Week | Team/Function | Owner | Experiment/Topic | Wins (What helped) | Challenges (What hindered) | Surprises/Insights | Quality & Trust Notes | Risks/Controls Needed | Artifacts/Links | Quotes (Participant Voice) | Metrics/Signals | Confidence (1-5) | Support Needed | Next Step & By When

## Prompts
Name | Prompt
Weekly Synthesis (Paste Feedback Rows) | You are an AI adoption coach. Synthesize this week’s entries from our Feedback table (pasted below). Create: (1) 5–7 bullet insights (wins, frictions, surprises), (2) a short risk/controls note, (3) 3 recommended experiments for next week with smallest viable scope, (4) one leader spotlight recognizing a specific contribution. Feedback rows: [[PASTE ROWS HERE]]
Executive One-Pager | Draft a crisp executive one-pager summarizing AI adoption progress for Week {{WEEK}}: Context, Highlights, Risks & Mitigations, Next Week Focus. Use plain language, 150–200 words, bullet-friendly.
Follow-up Email to Participants | Write a concise follow-up email to participants recapping Week {{WEEK}}. Sections: Thank you, What we learned (3 bullets), Decisions made, What to try before next session, How to ask for help. Friendly, pragmatic tone. 150–220 words. Subject line: ‘AI Sandbox Week {{WEEK}} — What’s Next’.
Pilot Candidate Selection | From the current Feedback data, propose 2–3 pilot candidates. For each: problem statement, expected benefit, minimal viable guardrails (reviewers, audit steps), and exit criteria. Keep each pilot description under 120 words.
Stakeholder Personas (Trust Builders) | Generate stakeholder personas for roles listed: {{ROLES}}. For each persona: motivation, specific concerns, trust builders (what they need to see/experience), and a 2-sentence engagement tactic.
Change Story (Before → After → Next) | Write a narrative of change: Before → After → Next, using highlights from the Feedback. Make it people-centered, credit contributors, and end with 3 specific next actions.